## LL feedback template
Lessons Learned Feedback Table
Feedback date: |  | Supplier Name:
Supplier responsible: |  | LL product/ process:
Risk evaluation | Is there any risk for occurrence of the same or similar failure? (Yes/No, with comments)
Is the failure related to any process in the LL receiving area? (Yes/No, please specify)
Does the risk assessment cover all potential risk points? (If yes, please list them)
Has the risk been evaluated for similar processes at sub- supplier(s) if neccesary? (Yes/No, with explanation if applicable)
Action plan | Have countermeasures been implemented to prevent failure occurrence? |  |  | R: | DD:
| Have countermeasures been implemented to improve failure detection? |  |  | R: | DD:
| Have countermeasures been applied to all relevant MAEs/processes? |  |  | R: | DD:
| Are there any additional countermeasures? (If yes, please specify) |  |  | R: | DD:
If no actions are taken, please provide a justification.
Sustainability/ effectiveness | Has the PFMEA been updated? |  |  | R: | DD:
| Has the Control Plan been updated? |  |  | R: | DD:
| Have relevant documents and work instructions (e.g., WI, SOPs) been updated? |  |  | R: | DD:
Signature after onsite process confirmation:
On site confirmed by BOSCH: (PQA/PQR/PQT) |  |  | Date:
Comments:

## Example
Lessons Learned Feedback Table
Feedback date: | 2025-03-06 | Supplier Name: | ABC
Supplier responsible: | ROBORT A | LL product/ process: | Plastic parts/DMC laser marking
Risk evaluation | Is there any risk for occurrence of the same or similar failure? (Yes/No, with comments) | Yes. If the root cause is not effectively addressed, similar marking quality issues may occur due to variations in molding surface conditions, laser power settings, or improper fixture positioning.
| Is the failure related to any process in the LL receiving area? (Yes/No, please specify) | No. The issue originates from the molding and laser marking process rather than the LL receiving area.
| Does the risk assessment cover all potential risk points? (If yes, please list them) | Yes. Identified risk points include: -Inconsistent surface texture of molded parts affecting laser contrast. -Variations in laser power and speed settings. -Fixture misalignment leading to improper marking positioning. -Inadequate quality inspection criteria for marking readability.
| Has the risk been evaluated for similar processes at sub- supplier(s)? (Yes/No, with explanation if applicable) | Yes. Similar marking issues have been observed in other molded parts. Sub-suppliers have been requested to review their process parameters and ensure consistent surface quality before marking.
Action plan | Have countermeasures been implemented to prevent failure occurrence? | Yes. Adjusted molding process parameters to ensure a more uniform surface finish before marking. |  | R: | ZZZ | DD: | yyyy-mm-dd
| Have countermeasures been implemented to improve failure detection? | Yes. Enhanced in-line inspection by implementing a vision system to check marking contrast and readability. |  | R: | ZZZ | DD: | yyyy-mm-dd
| Have countermeasures been applied to all relevant MAEs/processes? | Yes. Marking process validation and fixture standardization have been applied across all molding part marking stations. |  | R: | ZZZ | DD: | yyyy-mm-dd
| Are there any additional countermeasures? (If yes, please specify) | Yes. Introduced a periodic calibration check for laser marking machines. Updated training for operators on fixture positioning and marking criteria. |  | R: | ZZZ | DD: | yyyy-mm-dd
| If no actions are taken, please provide a justification. | N.A
Sustainability/ effectiveness | Has the PFMEA been updated? | Yes. Failure mode for DMC readability has been added with updated detection and prevention measures. |  | R: | ZZZ | DD: | yyyy-mm-dd
| Has the Control Plan been updated? | Yes. Marking process control parameters and inspection criteria have been revised. |  | R: | ZZZ | DD: | yyyy-mm-dd
| Have relevant documents and work instructions (e.g., WI, SOPs) been updated? | Yes. Operator work instructions now include a detailed marking verification process and troubleshooting guidelines. |  | R: | ZZZ | DD: | yyyy-mm-dd
Signature after onsite process confirmation:
On site confirmed by BOSCH: (PQA/PQR/PQT) |  |  | Date:
Comments:

## Document Change History
Document Change History
Version | Date | Reference | Description of Change | Status | Released by
1.0 | 09.Apr.2025 | LL Feedback | Initial version | valid | M/PUQ-ME-CN